OBTAIN PRE-CON APPROVALS

Document Control No	: 	VBHC/L&A/P/03

Revision No			:	Rev 1.1

Date of  Revision                    :  	31st August  2023

|  | Name/Designation | Signature | Date |
| --- | --- | --- | --- |
| Written By | Royal Reddy |  |  |
| Reviewed By | Kumar GVS |  |  |

HISTORY OF REVISIONS

| Revision No. | Revision Date | Chapter/clause no. & text affected | Reason for Revision |
| --- | --- | --- | --- |

TABLE OF CONTENTS

| SL No. | CONTENTS | PAGE NO. |
| --- | --- | --- |
| 1. | Purpose | 1 |
| 2. | Process Trigger | 1 |
| 3. | Scope and Application | 1 |
| 4. | Process Owner 5. | 1 |
| 5. | Successor and Predecessor | 1 |
| 6. | Responsibilities & Authorities | 1 |
| 7. | Definitions and Abbreviations | 1 |
| 8. | Process Flow Chart | 2 |
| 9. | Process Description | 2 |
| 10. | Efficiency measures and effectiveness measures | 5 |
| 11. | Risk associated with the process | 5 |
| 12. | Formats for maintaining records | 5 |
| 13. | Records | 5 |
| 14. | Annexure 1 | 6 |

OBTAIN PRE-CON APPROVALS

- PURPOSE

To define the required project specific approvals before the start of construction and to obtain them from an authorized body.

- PROCESS TRIGGER

This process is triggered after Master Plan is prepared.

- SCOPE AND APPLICATION

All VBHC projects.

- PROCESS OWNER

Head : Land Committee

- PREDECESSOR AND SUCCESSOR PROCESSER

Predecessor Process: Master Plan including phasing, concept and schematic (D,22)

Successor Process: Sales Planning and Launch (18, SM), Obtain approvals of Home Loans from Banks (29, SM)

- RESPONSIBILITY AND AUTHORITY

Preparation of Project Specific Approval List: Land Committee

- DEFINITIONS & ABBREVIATIONS

- PROCESS FLOW CHART

- PROCESS DESCRIPTION

  - For each project, depending on the State laws and regulations, the approvals required before construction will be different. A project specific list is prepared by the business head in consultation with the land department.

The list may include the following approvals:

TABLE 1: List of approvals required:

| S.No | Type of Approval | Approving Authority | Pre-requisites |
| --- | --- | --- | --- |
| 1. | Land Use Conversion | Development Authority/Municipality |  |
| 2. | NOC from Pollution Control Board/ Environmental Clearance | State Pollution Control Board and Ministry of Environment |  |
| 3. | NOC from Forest Department | Forest Department |  |
| 4. | Road Access Clearance before building plan approval | NHAI/PWD |  |
| 5. | AAI Height NOC( before building plan approval) | Civil Aviation Department |  |
| 6. | Building Layout Approval | Development Authority |  |
| 7. | Commencement Certificate | Development Authority/ Municipality |  |
| 8. | Fire fighting Scheme Approval | Chief Electrical Inspectorate of Govt |  |
| 9. | Lift Escalator Installation Approval ( wherever applicable) | Lift Inspectorate |  |
| 10. | Electric Substation NOC ( for all substations/transformers in the building) | State Electricity Board |  |
| 11. | DG Sets Installation approval | Chief Electrical Inspectorate |  |
| 12. | Certificate of clearance of all electrical installations in the building | State Electricity Board |  |
| 13. | Environment Clearance ( for 125 acres project with built up area above 20000sq metres) | Ministry of Environment and Forests |  |
| 14. | Bore well Registration Certificate | Central Groundwater Authority |  |
| 15. | Electrical Load/ Electrical Connection | State Electricity Board |  |
| 16. | Permission for Sewer Connection | Municipal Authority |  |
| 17. | Permission for Water Connection | Municipal Authority |  |
| 18. | Consent to Establish work at site | Pollution Control Board |  |

  - Once the list is prepared, the list is logically sequenced to find the interdependency between the approvals that are required.

  - Consultants are appointed by the land department head to assist with obtaining the approvals.

  - Approvals are applied for from the authorities respectively by the business head in the case consultants are not appointed, otherwise it is done by the consultants.

  - Any queries if raised by the authorities are resolved by business head ( for business related queries) and the respective discipline heads ( eg for queries related with electrical – electrical head , plumbing – plumbing head etc.)

  - Obtaining all the required approvals. This is informed to the top management and the head of departments. It is circulated internally by the business head and the land department.

- EFFECIENCY MEASURES AND EFFECTIVENESS MEASURES

Efficiency Measures:

Approvals are obtained in the scheduled time.

Number of queries due to incomplete documentation

Effectiveness Measures:

- RISK ASSOCIATED WITH THE PROCESS

If the approvals are not obtained, the occurrence of risks during the project phase might increase.

- FORMATS FOR MAINTAINING RECORDS GENERATED IN THE PROCESS

List of approvals for pre-construction

- RECORDS

ANNEXURE I

| Name of Format | Code |
| --- | --- |
| List of approvals for pre-construction | VBHC/L&A/F/01 |