PRE-CONSTRUCTION HR PLANNING

Document Control No	: 	VBHC/OPE/P/06

Revision No			:	Rev 1.1

Date of  Revision                    :  	31st August 2023

|  | Name/Designation | Signature | Date |
| --- | --- | --- | --- |
| Written By | Shivaprasad |  |  |
| Reviewed By | Kumar GVS |  |  |

HISTORY OF REVISIONS

| Revision No. | Revision Date | Chapter/clause no. & text affected | Reason for Revision |
| --- | --- | --- | --- |

TABLE OF CONTENTS

| SL No. | CONTENTS | PAGE NO. |
| --- | --- | --- |
| 1. | Purpose | 1 |
| 2. | Process Trigger | 1 |
| 3. | Scope and Application | 1 |
| 4. | Process Owner 5. | 1 |
| 5. | Successor and Predecessor | 1 |
| 6. | Responsibilities & Authorities | 1 |
| 7. | Definitions and Abbreviations | 1 |
| 8. | Process Flow Chart | 2 |
| 9. | Process Description | 2 |
| 10. | Efficiency measures and effectiveness measures | 3 |
| 11. | Risk associated with the process | 3 |
| 12. | Formats for maintaining records | 3 |
| 13. | Records | 3 |
| 14. | Annexure 1 | 4 |

PRE-CONSTRUCTION HR PLANNING

- PURPOSE

To Identify and estimate man-power resource requirement for execution of the project with desired skill sets based on PMS prepared for the project

- PROCESS TRIGGER

This process is triggered when Project Master Schedule for the project is approved by the COO.

- SCOPE AND APPLICATION

This process applies to all VBHC projects and cover planning for human resources to be deployed at the project site on permanent pay roll of VBHC.

- PROCESS OWNER

PMC - Head.

- PREDECESSOR AND SUCCESSOR PROCESSES

Predecessor Process: Project Master Schedule (P30,PMC)

Successor Process: Recruitment (P48,HR)

- RESPONSIBILITY AND AUTHORITY

To prepare HR Schedule	: Head – PMC.

- DEFINITIONS & ABBREVIATIONS

- PMS		: 	Project Master Schedule.

- PMC		: 	Project Management.

- HR Planning	: 	Human Resource Planning

- COO		:	Chief Operating Officer

- PROCESS FLOW CHART

- PROCESS DESCRIPTION

- Project Master Schedule: Provides the input for the resource requirement.

- Identify the requirement department wise: PMC shall then estimate total man-power requirement department-wise for the project.

- Preparation of Manpower requirement: The department wise manpower requirement then tabulated (Refer attachment).Which details designation, qualification, experience and expected date of joining of the staff.

- Recruitment: HR department shall then initiate the man-power recruitment as per the inputs.

- EFFECIENCY MEASURES AND EFFECTIVENESS MEASURES

Efficiency Measures: The fresh hiring inputs shall be given to HR department 60days before the actual requirement at site.

Effectiveness Measures:

Number of changes made in HR requirements of a project vis-à-vis the HR plan at pre – construction stage

- RISK ASSOCIATED WITH THE PROCESS

Availability of man-power and availability of desired skill sets.

- FORMATS FOR MAINTAINING RECORDS GENERATED IN THE PROCESS

  - Manpower requirement table:

| Sl. No | Designation | Qualification | Experience | Expected date of Joining |
| --- | --- | --- | --- | --- |

- RECORDS

ANNEXURE I

| Name of Format | Code |
| --- | --- |
| Manpower requirement table | VBHC/OPE/F/04 |