GFC GENERATION

Document Control No	: 	VBHC/DES/ /05

Revision No			:

Date of  Revision                    :

|  | Name/Designation | Signature | Date |
| --- | --- | --- | --- |
| Reviewed By |  |  |  |
| Approved By |  |  |  |

TABLE OF CONTENTS

| SL No. | CONTENTS | PAGE NO. |
| --- | --- | --- |
| 1. | Purpose | 1 |
| 2. | Process Trigger | 1 |
| 3. | Scope and Application | 1 |
| 4. | Process Owner 5. | 1 |
| 5. | Successor and Predecessor | 1 |
| 6. | Responsibilities & Authorities | 1 |
| 7. | Definitions and Abbreviations | 2 |
| 8. | Process Flow Chart | 2 |
| 9. | Process Description | 5 |
| 10. | Efficiency measures and effectiveness measures | 14 |
| 11. | Risk associated with the process | 14 |
| 12. | Formats for maintaining records | 14 |
| 13. | Records | 14 |
| 14. | Annexure I | 15 |

GFC GENERATION

- PURPOSE

To generate Good-For-Construction (GFC) drawings for use by Estimation Dept (for Quantification & subsequent costing) and Site Engineers for actual execution

- PROCESS TRIGGER

This process is triggered when Sanction Drawings are complete and informal review has been received from the authorities.

- SCOPE AND APPLICATION

Applicable to all projects developed by VBHC

- PROCESS OWNER

Design Head

## PREDECESSOR AND SUCCESSOR PROCESSES

## Predecessor: Obtain Pre-Con Approvals (P18, L)

## Successor:  Prepare Project Budget R2 (P27, Est.), Daily Construction Management (P41,OP), Procure Contractors (P&C,P29)

## RESPONSIBILITY AND AUTHORITY

## Lead Architect and Service heads Responsible for respective GFC generation

## Technical sign-off from Design Head

## Final signoff by the Estimation and Execution heads

## DEFINITIONS & ABBREVIATIONS

## GFC – Good for Construction

## PROCESS FLOW CHART

8.1 BUILDING GFC GENERATION (NEW UNIT / BLOCK PROTOTYPE)

8.2 GENERATION OF ELECTRICAL INFRA GFC’S

8.3 GENERATION OF PHE INFRA GFC’S

## PROCESS DESCRIPTION

  - BUILDING GFC GENERATION (NEW UNIT / BLOCK PROTOTYPE)

9.1.1This process is triggered, when a new unit or block is to be designed.

9.1.2 The architect designs the unit or block and details out the architectural plans, sections and elevations. These are used as inputs by the structural and plumbing team to decide upon the structure as well as to prepare conceptual drawings and levels.

9.1.3 The architectural, structural, electrical, fire and plumbing team work together to detail and create drawings on software such as AutoCAD Revit, specifications and BoQ. These are sent to site and estimation department for review. The release of the drawings are recorded in the drawings release register.

9.1.4 Once the feedback is obtained, the architectural, structural, electrical, plumbing and fire produce the final GFC’s along with BoQ and final specs.

9.1.5 The final GFC’s BoQs and final specs are added into the catalog. (A catalog is a collection of drawings from previous projects)

Table 1: List of Architectural GFC’s

| Sl No | Drawing Name |
| --- | --- |
| 1 | Cover Sheet |
| 2 | Ground and Typical Floor Plan |
| 3 | Terrace and OHT level plan |
| 4 | Elevations |
| 5 | Sections |
| 6 | Ground Floor-Floor Finish Detail |
| 7 | Typical Floor - Floor Finish Detail |
| 8 | False Ceiling Plan Ground Floor |
| 9 | Finishes Schedule |
| 10 | Staircase Detail |
| 11 | Staircase and Lift Elevation |
| 12 | Entrance Lobby Details and Ramp Details |
| 13 | Railing Detail for Staircase |
| 14 | Railing Details for Lobby and Corridor |
| 15 | Balcony Details and Details at Window W1 |
| 16 | Toilet Details |
| 17 | Kitchen Details |
| 18 | Door Schedule and Details |
| 19 | Window, Ventilator Schedule and Details |
| 20 | MS Door Details |

Table 2 : List of Electrical GFC’s ( Units/ Blocks )

| Sl No | Drawing Name |
| --- | --- |
| 1 | Model Apartment Electrical Layout |
| 2 | Basement Floor Cable Tray Layout |
| 3 | Basement Floor Electrical Layout |
| 4 | Stilt/Ground Floor Cable Tray Layout |
| 5 | Stilt/Ground Floor Electrical Layout |
| 6 | First Floor Electrical Layout |
| 7 | Typical Floor Electrical Layout |
| 8 | Terrace Floor Electrical Layout |
| 9 | Lightning Arrestor & L.M.R Electrical Layout |
| 10 | Typical Flat Electrical Layout (1BHK ) |
| 11 | Typical Flat Electrical Layout (2BHK ) |
| 12 | Typical Flat Electrical Layout (3BHK ) |
| 13 | Typical Flat Electrical Layout (Studio) |

Table 3: List of  Plumbing GFC’s ( Units/ Blocks )

| Sl No | Drawing Name |
| --- | --- |
| 1 | Enlarged Toilet Details |
| 2 | Enlarged Kitchen Details |
| 3 | Stilt ceiling plumbing layout |
| 4 | Ground and typical floor plumbing layout |
| 5 | Terrace Floor water supply plan |
| 6 | Terrace Floor rain water drainage |
| 7 | OHT details |
| 8 | Schematic Water Supply ( Block Wise ) |
| 9 | Lightning Arrestor & L.M.R Electrical Layout |

Table 4: List of Structural GFCs

| Sl No | Drawing Name |
| --- | --- |
| 1 | General Notes |
| 2 | Standard Details |
| 3 | Column layout |
| 4 | Column layout with location details |
| 5 | Foundation layout and RC details |
| 6 | Foundation section details |
| 7 | Plinth beam layout and section details |
| 8 | Ground floor shuttering and section details |
| 9 | First floor shuttering layout and section details |
| 10 | Second floor shuttering layout and section details |
| 11 | Typical floor shuttering layout and section layout |
| 12 | Terrace floor shuttering layout and section details |
| 13 | Above terrace floor shuttering layout |
| 14 | Lift and staircase head room shuttering layout |
| 15 | Column schedule and lift core details |
| 16 | Column schedule and lift core details |
| 17 | Column schedule and lift core details |
| 18 | Plinth beam RC details |
| 19 | Ground floor beam RC details |
| 20 | First floor beam RC details |
| 21 | Second floor beam RC details |
| 22 | Typical floor RC details |
| 23 | Terrace floor RC details |
| 24 | Wall elevations and RC details |
| 25 | Ground floor slab RC details- bottom reinf. |
| 26 | Ground floor slab RC details-top reinf. |
| 27 | First floor slab RC details- bottom reinf. |
| 28 | First floor slab RC details-top reinf. |
| 29 | Second floor slab RC details- bottom reinf. |
| 30 | Second floor slab RC details-top reinf. |
| 31 | Typical floor slab RC details- bottom reinf. |
| 32 | Typical floor slab RC details-top reinf. |
| 33 | Terrace floor slab RC details-bottom reinf. |
| 34 | Terrace floor slab RC details-top reinf. |
| 35 | Staircase layout and RC details |
| 36 | Compound wall details |
| 37 | UG sump shuttering and RC details |
| 38 | Retaining wall RC details |
| 39 | Ramp RC details |
| 40 | Drain RC details |
| 41 | Drain RC cover slab detail |

9.2 GENERATION OF ELECTRICAL INFRA GFC’S

9.2.1 The lead architect will provide the electrical design team with the master plan with service area location, levels, road profiles, road sections, building plans and sections. Depending on whether it is 3 or 5 KVA connection, the following are decided upon:

- Total Electrical capacity needed\

- Max Elec Room Fixed

- Transformer Location and Size

- DG Location

- Elec- Shaft Location

9.2.2 Electrical Drawings are prepared by the electrical architect using software such as AutoCAD Revit.

9.2.3 The lead architect, the electrical architect and the electrical design team review drawings and suggest changes if required.

9.2.4 All changes are carried out and the GFC drawings are finalized.

Table 5 : List of  Electrical Infra GFC’s

| Sl No | Drawing Name |
| --- | --- |
| 1 | Main Single Line Diagram |
| 2 | LT Cable routing Layout |
| 3 | External Lighting Layout |
| 4 | Transformer yard Equipment & Equipment Foundation Layout |
| 5 | Earthing Layout |

9.3 GENERATION OF PLUMBING INFRA GFC’S

9.3.1 The lead architect will provide the plumbing design team with the master plan with levels, road profiles, road sections, bore well location, landscape plan, building plans and sections. The following are decided upon:

- Area statement

- Size and location of UG sump

- Size and location of STP

- Size  of OHT, Fire OHT and Flush

- No of Tanks

- No of Sumps.

9.3.2 The following are designed by the plumbing architect.

- Water Supply Network

- Water Automation System

- Pressurised/Non pressurised

- Borewell interconnection scheme

- RWH

- Sewage and storm water network Electrical Drawings are prepared by the electrical architect using software such as AutoCAD Revit.

9.3.3 The lead architect, the electrical architect and the electrical design team review drawings and suggest changes if required.

9.3.4 All changes are carried out and the GFC drawings are finalized.

Table 6 : List of  Plumbing Infra GFC’s

| Sl No | Drawing Name |
| --- | --- |
| 1 | Site Plan - External Storm Water Layout |
| 2 | Site Plan - External Sewer Drainage Layout |
| 3 | Site Plan - External Water Supply Layout |
| 4 | Site Plan - External Coordination Layout |
| 5 | U.G Sump and Pump Room details |
| 6 | S.T.P Location and Details |

Table 7 : Summary of the process

| # | Sub-Process Name | Business Impact of the Process | Inputs | Design Output | Reviewed and Approved By |
| --- | --- | --- | --- | --- | --- |
| 1 | Architectural Design | Arch-GFCs (for execution & estimation) | 1.) Unit & Block Plans 2.) Road & Plinth Levels 3.) Approved Specs, Brands & Dimensions 4.) Approved Unit Configuration List 5.) Structural Input 6.) Services Inputs | 1.) 1st-Cut Dwgs to be shared with Structural Consultant 2.) Architectural GFCs | Lead Architect |
| 2 | Structural Design | Stru-GFCs (for execution & estimation) | 1.) 1st-Cut Arch-Dwgs 2.) Architectural GFCs 3.) Soil-Test Reports 4.) Levels 5.) Service Inputs (Plumbing - Bldg & Infra) | 1.) 1st-cut Framing Dwgs to be shared with VBHC-Services 2.) Framing GFCs 3.) Reinforcement GFCs 4.) Stru-Infra GFCs 5.) BoQ | Consultant and Head- Design |
| 3 | Electrical Design | Elec-GFCs (for execution & estimation) | 1.) 1st-Cut Arch-Dwgs 2.) Approved Unit-Configuration List 3.) Master Plan 4.) Road Drawings with Levels & Sections 5.) Electrical Infra Survey Report (for tapping point etc.) 6.) Drawings & Documentation from Lift-Vendor | 1.) Electrical GFCs (Bldg & Infra) | Head-Electrical |
| 4 | Electrical BoQ & Estimation | Elec-BoQ (for execution & estimation) | 1.) Electrical GFCs (Bldg & Infra) 2.) Approval Specs & Brands | 1.) BoQs (Material List with Rates) | Head-Electrical |
| 5 | PHE Design | PHE-GFCs (for execution & estimation) | 1.) 1st-Cut Arch-Dwgs 2.) Approved Unit-Configuration List 3.) Master Plan 4.) Road Drawings with Levels & Sections 5.) PHE Infra Survey Report (for tapping point etc.) 6.) Stru-Framing Drawings | 1.) PHE GFCs (Bldg & Infra) 2.) Input to be given to STP Vendor | Head- Plumbing |
| 6 | Roads & Levels | Roads & Excavation GFCs (for execution & estimation) | 1.) Master Plan 2.) Soil Report 3.) Topo Survey | 1.) Master Plan with Road Levels & Cross-Sections 2.) Road Profiles 3.) Retaining Walls 4.) Excavation Dwgs (as necessary) 5.) Cut/Fill Volumes | Head- BIM |
| 7 | Landscape Design | Landscape-GFCs (for execution & estimation) | 1.) Master Plan 2.) Natural & Finished Ground Levels 3.) Service-Coordination Dwgs 4.) Landscape Plan | 1.) Landscape GFCs | Head- BIM |

The release of these drawings are recorded in the drawings release register, while the status of the drawings are recorded in the weekly progress report.

The drawings are released on to site along with transmittal

## CODIFICATION OF DRAWINGS

A unique companywide document codification system to ensure proper identification and traceability of origin of drawings has been established. The following steps describe the document codification system:

- An alphanumeric system containing both alphabets and numbers has been developed for codifying the drawings originated from the design department.

i.e VBHC/ PROJECT CODE/LOCATION / TYPE OF DWG / PURPOSE / DRAWING No/ Rn

10.1 Project Code will denote the code of the project :

| Project Name | Project Code |
| --- | --- |
| Kengeri 2 | KEN 2 |
| Kannamangala | KAN |

**Codes will be added upon with upcoming projects

10.2 Location code indicates the location the drawing refers to on site :

| Location | Location Code |
| --- | --- |
| Cluster | CLS |
| Block No ( e.g BLK A2) | BLK # |
| Infrastructure | INF |
| Amenities | AME |
| Temporary Structure | TM |

10.3 Type of Drawing denotes whether the drawings is an architectural or plumbing or electrical or landscape drawings

| Type of Drawing | Code |
| --- | --- |
| Architecture | A |
| Plumbing | P |
| Electrical | E |
| Landscape | L |

10.4 Purpose indicates the purpose of the drawing.

| Purpose | Code |
| --- | --- |
| Preliminary | PLR |
| Sanction | SNC |
| Airport | AIR |
| MoEF | MOF |
| Good for Construction | GFC |
| BWSSB | BWS |
| BESCOM | BES |
| Pollution Control Board | PCB |

10.5 Drawing No will denote the number of the drawings

10.6 Rn – Rn refers to the revision number .

## EFFECIENCY MEASURES AND EFFECTIVENESS MEASURES

Efficiency measures: Number of RFIs received per drawing

Number of revisions required

Effectiveness measures: Time taken to release all GFC from trigger

## RISK ASSOCIATED WITH THE PROCESS

## FORMATS FOR MAINTAINING RECORDS GENERATED IN THE PROCESS

Transmittals

## RECORDS

Drawings Release Register

ANNEXURE 1

| Name of Format | Code |
| --- | --- |
| - Transmittals | VBHC/DES/SW/05 |