PRE-CONSTRUCTION SITE PRELIMINARIES

Document Control No	: 	VBHC/OPE/P/01

Revision No			:	Rev 1.1

Date of  Revision                    :  	31st August 2023

|  | Name/Designation | Signature | Date |
| --- | --- | --- | --- |
| Written By | Shivaprasad |  |  |
| Reviewed By | Kumar GVS |  |  |

TABLE OF CONTENTS

| SL No. | CONTENTS | PAGE NO. |
| --- | --- | --- |
| 1. | Purpose | 1 |
| 2. | Process Trigger | 1 |
| 3. | Scope and Application | 1 |
| 4. | Process Owner 5. | 1 |
| 5. | Successor and Predecessor | 1 |
| 6. | Responsibilities & Authorities | 1 |
| 7. | Definitions and Abbreviations | 2 |
| 8. | Process Flow Chart | 2 |
| 9. | Process Description | 2 |
| 10. | Efficiency measures and effectiveness measures | 3 |
| 11. | Risk associated with the process | 3 |
| 12. | Formats for maintaining records | 3 |
| 13. | Records | 3 |
| 14. | Annexure 1 | 4 |

PRECONSTRUCTION SITE PRELIMINARIES

- PURPOSE

To conduct and implement all pre construction site preliminary activity prior to the construction of the project.

- PROCESS TRIGGER

The process is triggered once the project master schedule is prepared and prior to construction.

- SCOPE AND APPLICATION

All VBHC projects

- PROCESS OWNER

Head: Operation

- PREDECESSOR AND SUCCESSOR PROCESSES

Predecessor: Project Master Schedule (P30,PMC)

Successor: Pre-Construction Monitoring (P32,PMC), Health and Safety Management (P55,OP).

- RESPONSIBILITY AND AUTHORITY

- Charting out activities: Operations Department in consultation with the Business head

- Listing out all the equipment needed for the implementation : PMC department

- Approval of indents / requisitions :Business Head

- Purchase of all required items : Purchase Department

- DEFINITIONS & ABBREVIATIONS

- PROCESS FLOW CHART

- PROCESS DESCRIPTION

  - The preconstruction financial plan is received from the financial department

  - All the preconstruction that needs to take place before the construction starts are charted out by the operations department in consultation with the Business head.

  - All the items ( i.e. materials, equipment etc) to implement the pre construction activities are purchased by the P&C department after receiving the indents from the PMC department with the approval of the business head.

  - All the facilities that are required are set up as per the schedule.

Following are the preconstruction facilities to be set up:

- Boundary wall

- Government Survey

- Marketing office portacabin

- Soft and hard Landscaping of marketing area

- Sample apartment

- Picket fence separating sample apartment from construction area

- Internet connectivity for marketing office

- Procurement of desktops, cafeteria for marketing office

- Setting up of washroom with soak pit

- Electrical connection of 10 KVA

- Stores Portacabin

- Security kiosk with toilets

- Labour Colony

- I.T Set up

10. EFFECIENCY MEASURE AND EFFECTIVENESS MEASURE

Efficiency Measures:

Effectiveness Measures: Actual vs scheduled completion

- RISK ASSOCIATED WITH THE PROCESS

- FORMATS FOR MAINTAINING RECORDS GENERATED IN THE PROCESS