R2 BUDGET

Document Control No	: 	VBHC/EST/P/02

Revision No			:	Rev 1.1

Date of  Revision                    :  	31st August 2023

|  | Name/Designation | Signature | Date |
| --- | --- | --- | --- |
| Written By | Azhar Ahmad |  |  |
| Reviewed By | Kumar GVS |  |  |
| Approved By |  |  |  |

HISTORY OF REVISIONS

| Revision No. | Revision Date | Chapter/clause no. & text affected | Reason for Revision |
| --- | --- | --- | --- |

TABLE OF CONTENTS

| SL No. | CONTENTS | PAGE NO. |
| --- | --- | --- |
| 1. | Purpose | 1 |
| 2. | Process Trigger | 1 |
| 3. | Scope and Application | 1 |
| 4. | Process Owner 5. | 1 |
| 5. | Successor and Predecessor | 1 |
| 6. | Responsibilities & Authorities | 1 |
| 7. | Definitions and Abbreviations | 1 |
| 8. | Process Flow Chart | 2 |
| 9. | Process Description | 3 |
| 10. | Efficiency measures and effectiveness measures | 3 |
| 11. | Risk associated with the process | 3 |
| 12. | Formats for maintaining records | 3 |
| 13. | Records | 3 |
| 14 | Annexure I | 4 |

R2 BUDGET

- PURPOSE

To calculate final construction cost based on GFC drawings.

- PROCESS TRIGGER

GFC’s from Design Team

- SCOPE AND APPLICATION

This process is applicable to all ongoing and new projects of VBHC.

- PROCESS OWNER

Head – Estimation

- PREDECESSOR AND SUCCESSOR PROCESSES

Predecessor Process: GFC Generation (D)

Successor Process:  Budget Tracking, Cost Control and Revisions ( EST), Procure Materials (P&C), Appoint Contractors (P&C),Site Coordination (PMC)

- RESPONSIBILITY AND AUTHORITY

Approval of Budget	:	COO

- DEFINITIONS & ABBREVIATIONS

- URA		: Unit Rate Analysis

- P&C Dept	: Procurement and Contracts Department

- BOQ		: Bill of Quantities

- COO		: Chief Operations Officer

- PROCESS FLOW CHART

- PROCESS DESCRIPTION

  - Following inputs are received by Estimation dept. from other departments:

    - Master Plan, Specifications, GFC’s (Architectural and Structural) from Design team. (some infrastructure design may not be available in full detail)

    - Material/Labour rates and sub- contractor rates from P & C dept. (Estimation team can override the inputs received from P & C.)

  - Quantification and URA are prepared by Estimation dept. based on inputs received.

  - Project budget is prepared by Estimation dept. and the same is presented in Estimation Review Meeting to COO.

  - If any changes are recommended by COO, then

    - For estimation changes (Quantification /URA) revision of Quantification /URA is done and project budget is prepared by Estimation dept.

    - For Design changes, the Design team is intimated for changes in specifications/drawings by Estimation dept. The new inputs are considered for further budget preparation by Estimation dept.

  - The budget approved by COO  is R2 budget for :

- Building

- Infra.

- EFFECIENCY MEASURES AND EFFECTIVENESS MEASURES

Efficiency Measures: Deviation between R1 and R2 Budget

Effectiveness Measures: Number of days taken to release R2 budget from the trigger

- RISK ASSOCIATED WITH THE PROCESS

This budget is prepared using all the available information. Limited risk can be because of, unanticipated price increase and infrastructural details that are not finalised at this budgeting.

- FORMATS FOR MAINTAINING RECORDS GENERATED IN THE PROCESS

R2 Budget

- RECORDS

Record of R1 & R2 Budgets – Minimum Retention Period – Till Project Completion

- ANNEXURE I;

| Name of Format | Code |
| --- | --- |
| R2 Budget | VBHC/EST/F/02 |