DAILY CONSTRUCTION MANAGEMENT

Document Control No	: 	VBHC/OPE/P/02

Revision No			:	Rev 1.1

Date of  Revision                   :  	31st August 2023

|  | Name/Designation | Signature | Date |
| --- | --- | --- | --- |
| Written By | Shivaprasad |  |  |
| Reviewed By | Kumar GVS |  |  |

HISTORY OF REVISIONS

| Revision No. | Revision Date | Chapter/clause no. & text affected | Reason for Revision |
| --- | --- | --- | --- |

TABLE OF CONTENTS

| SL No. | CONTENTS | PAGE NO. |
| --- | --- | --- |
| 1. | Purpose | 1 |
| 2. | Process Trigger | 1 |
| 3. | Scope and Application | 1 |
| 4. | Process Owner 5. | 1 |
| 5. | Successor and Predecessor | 1 |
| 6. | Responsibilities & Authorities | 1 |
| 7. | Definitions and Abbreviations | 1 |
| 8. | Process Flow Chart | 2 |
| 9. | Process Description | 3 |
| 10. | Efficiency measures and effectiveness measures | 4 |
| 11. | Risk associated with the process | 4 |
| 12. | Formats for maintaining records | 4 |
| 13. | Records | 7 |
| 14. | Annexure I | 8 |

DAILY CONSTRUCTION MANAGEMENT

- PURPOSE

To establish a process for daily construction management

- PROCESS TRIGGER

This process is carried out daily at the construction site.

- SCOPE AND APPLICATION

This procedure applies to all the construction activities carried at VBHC.

- PROCESS OWNER

Assistant Manager, Operations.

- PREDECESSOR AND SUCCESSOR PROCESSES

Predecessor Process:

Successor Process:

- RESPONSIBILITY AND AUTHORITY

- DEFINITIONS & ABBREVIATIONS

- AGM			: Assistant General Manager

- MOM			: Minutes of Meeting

- MR			: Management Representative

- PROCESS FLOW CHART

- PROCESS DESCRIPTION

  - Project Management team updates the monthly schedule to the master schedule.

  - Monthly Schedule is prepared by Asst. Manager - Operations, every month last working day he submits the next month’s schedule to AGM – Construction for review.

  - AGM – Construction reviews the schedule on the same or the very next day, and if found necessary shall suggest any changes in the schedule to Asst. Manager - Operations.

  - After the changes done by Asst. Manager – Operations the schedule is approved by AGM – Construction.

  - After the approval by AGM construction, intimation is given to PMC dept and Managers/Engineers who handle the respective activities through email.

  - Asst. Manager/Sr. Project Manager checks for the execution of activities in sequence (steel, Plumbing, Electrical etc.,) and if any corrections observed, intimation is given to incharge of the activity.

  - Asst. Manager/Sr. Project Manager daily updates the completed activities and intimates about the same to AGM, PMC team and Concern Managers/Engineers.

  - Project Management team updates Master Schedule, the planned vs Actual Progress and the remarks every month, intimates the same to Operations dept. through email.

  - AGM Construction with all the Managers and Block Incharges conducts daily Review Meeting. The following issues are discussed during meeting:

- Updating daily work done

- Reasons for lags in the schedule if any.

- Any issues/problems at site which affects the work schedule.

- Possible solutions to overcome the issues/problems

  - Project Management team at site prepares and maintains the MOM for every review meeting.

  - If the issues/Problems cannot be resolved, then it is escalated to AGM – Construction, AVP and TOP Management by Project Management team.

  - If the issues/Problems can be resolved, then solution is applied and monitored by Asst. Manager/Sr. Project Manager

- EFFECIENCY MEASURES AND EFFECTIVENESS MEASURES

Efficiency Measures:

Effectiveness Measures: Planned Vs Actual Progress

- RISK ASSOCIATED WITH THE PROCESS

- FORMATS FOR MAINTAINING RECORDS GENERATED IN THE PROCESS

Master Schedule

- RECORDS

Minutes of Meeting – Minimum Retention Period – 1Yr

ANNEXURE I.

| Name of Format | Code |
| --- | --- |
| Master Schedule | VBHC/OPE/F/01 |