UPDATE CONSTRUCTION SCHEDULE

Document Control No	: 	VBHC/PMC/P/03

Department			:	PMC

Revision No			:	Rev 1.0

|  | Name/Designation | Signature | Date |
| --- | --- | --- | --- |
| Written By | Shivaprasad |  |  |
| Reviewed By | Kumar GVS |  |  |

HISTORY OF REVISIONS

| Revision No. | Revision Date | Chapter/clause no. & text affected | Reason for Revision |
| --- | --- | --- | --- |

TABLE OF CONTENTS

| SL No. | CONTENTS | PAGE NO. |
| --- | --- | --- |
| 1. | Purpose | 1 |
| 2. | Process Trigger | 1 |
| 3. | Scope and Application | 1 |
| 4. | Process Owner 5. | 1 |
| 5. | Successor and Predecessor | 1 |
| 6. | Responsibilities & Authorities | 1 |
| 7. | Definitions and Abbreviations | 1 |
| 8. | Process Flow Chart | 2 |
| 9. | Process Description | 2 |
| 10. | Efficiency measures and effectiveness measures | 3 |
| 11. | Risk associated with the process | 3 |
| 12. | Formats for maintaining records | 3 |
| 13. | Records | 3 |
| 14. | Annexure 1 | 4 |

UPDATE CONSTRUCTION SCHEDULE

- PURPOSE

To update and track the progress with respect to the PMS

- PROCESS TRIGGER

This process is triggered when project master schedule is approved.

- SCOPE AND APPLICATION

Identification of possible Challenges; providing mitigation plan; plan parallel and independent activities to minimize lags in the project; identification of critical path

- PROCESS OWNER

PMC - Head.

- PREDECESSOR AND SUCCESSOR PROCESSES

Predecessor Process	:Pre Con and Construction Monitoring (P27,PMC)

Successor Process	: Pre Con and Construction Monitoring (P27,PMC), Site Coordination (P29,PMC)

- RESPONSIBILITY AND AUTHORITY

To update construction schedule: PM - Manager.

- DEFINITIONS & ABBREVIATIONS

PMS: Project Master Schedule.

PMC: Project Management.

- PROCESS FLOW CHART

- PROCESS DESCRIPTION

  - The Weekly progress report generated and published weekly in the process Pre – construction and construction monitoring, is a source for tracking delay.

  - The delay is calculated based on actual % upon planned %. It is indicatively reported in the Weekly Progress report with the use of different colours.

  - If the delay is less than the allowable limit (20% - activity wise), the percentages are highlighted in yellow. If the delay is more than 20%, the percentages are highlighted in red. If actual % is equal to planned %, it is highlighted in green. If for a block, the work is on hold, it is highlighted in blue.

  - If delay is less than allowable limit (20% - activity wise), the construction schedule remains unchanged.

  - Risk Mitigation Plan: If delay is greater than allowable limit, the delay is analyzed and risk mitigation plan is reported in the Weekly Progress report itself.

  - Update Construction Schedule: In cases of delay, the construction schedule is updated on Microsoft Project (MSP) tool as per the risk mitigation plan. The projected dates for the activities are anticipated.

  - Report generation & distribution: The MSP is uploaded on the server.

- EFFECIENCY MEASURES AND EFFECTIVENESS MEASURES

Efficiency Measures:	Number of days taken to update the schedule from the time 20% delay is established

Effectiveness Measures:

- RISK ASSOCIATED WITH THE PROCESS

Failure to update the schedule may affect other planning processes making resource deployment ineffective

- FORMATS FOR MAINTAINING RECORDS GENERATED IN THE PROCESS

Project Master Schedule format

- RECORDS

Updated Schedule ( MSP file )

ANNEXURE I

| Name of Format | Code |
| --- | --- |
| Weekly Progress Report | VBHC/PMC/F/04 |